## Slide 1: Planning – Proposal, Estimation & WBS
邹欣
构建之法 – 现代软件工程

## Slide 2: Agenda
Proposal
Estimation
Roles for Each Team Member
WBS
Class Exercise

## Slide 3: NABC model
1) N (Need 需求)
你的创意解决了用户的什么需求?
我们要充分了解用户的痛苦, 他们对已有软件, 服务不满意的地方。但是用户往往也不知道颠覆型的创新
2) A (Approach 做法)
你有什么招数, 特别是独特的招数, 来解决用户的痛苦。
这些招数不光是技术上的, 也可以是商业模式上的, 地域的, 人脉的, 行业的.
3) B (Benefit 好处)
那你这个产品/服务会给客户/用户带来什么好处呢?
Benefit/Cost (成本) 的问题。
4) C (Competitors 竞争)
竞争对手也没有闲着, 这个市场有多大, 目前有多少竞争者在瓜分, 你了解么? 你如果不是最先进入某个市场的产品, 你还能赢么?
5) D (Delivery)
你怎么让目标用户都知道你的产品? 并且让产品的用户量快速提高?

## Slide 4: Project Proposal
Group Exercise, for your project
What’s the history of innovation in this area?
Is your project the 1st mover, 2nd mover or Nth Mover?
What’s sustaining technology, performance oversupply, and disruptive technology in this area?
Any unaddressed “user need” still out there?
What is “success” for such project? Why your product can win?
How to win in 3-6 month?
One person from each group to give us a report

## Slide 5: Elevator Pitch
For <target customer: Persona>
  who < customer Need>
Our product <name> is a <product category>
  that <key Benefit, compelling reason to buy>.
Unlike <primary Competitive alternative>
  our product <primary differentiation, Approach>.
We can quickly reach our target users via
  Delivery.

## Slide 6: Rough Feature List
For the Alpha release
  Release date: week #8
  You can pick a day during the week as your release day.
For Beta release
  Release date: week #13
  You can pick a day during the week as your release day.

## Slide 7: Estimation
电视剧里, 抗战前夕, 主人公讲 “长达八年的抗日战争开始了”...
未卜先知!
Notes: <情深深雨蒙蒙>，第四十一集
书桓

## Slide 8: Estimation
Foundation of collaboration
  Is to estimate task cost for you and your teammates
These are different things:
  Target (目标)
  Commitment (决心)
  Estimation (估计)
Notes: Gf might as an extra hour to prepare herself

## Slide 9: Estimation/Target/Commitment
Target (目标)
  A statement of a desirable business objective
  “We need to have v1 released on ____”
  A business target is independent of software estimates
  A target is desirable, or mandatory DOESN’T mean it’s achievable
Commitment (决心)
  It’s a promise to deliver pre-defined functionality as specific level of quality by a certain date
Estimation (估计)
  How long a task will take or how much it will cost, with a limit set of resources
Notes: Gf might as an extra hour to prepare herself

## Slide 10: Target - Historical Example
1958年5月中共八大二次会议肯定了当时中国出现的“大跃进”形势，认为中国正经历着“一天等于二十年”的伟大时期。调整了“二五”计划指标，钢产量由1200万吨提高到3000万吨，粮食从5000亿斤上升到7000亿斤。提出要使中国在15年或更短的时间内，在主要工业产品产量方面在十年内超过英国、十五年内赶美国（所谓“超英赶美”）。从此，“大跃进”在中国大陆全面展开。农业要“以粮为纲”，要求5年、3年甚至1－2年达到12年发展纲要规定的指标。工业则“以钢为纲”，将赶超英国的目标缩短为7年、5年以至3年。
毛泽东在批语中写道：“赶超英国，不是十五年，也不是七年，只需要两年到三年，两年是可能的。”
大跃进开展只过了半年的时间，中共中央便把赶超英国的时间由十五年改为两年。
1977 年, 中国钢产量超过英国。 用了19 年时间。

## Slide 11: More on Target (目标)
A project can be driven on
  Time (must finish it by certain date)
  Feature (must have these features before it’s done)
  Budget/Resource (will end the project when we use up our budget)
Desiderata (需求, 必需品)
  Fast (快)
  Good (多, 好)
  Cheap (省)
These three things can’t always be satisfied at the same time
  多快好省地建设社会主义 – 大跃进
  达到了”快”, “多, 好, 省” – 没达到.
  事实上, 也没有 “快”.
Exercise
  List real life examples

## Slide 12: Our project is
Time driven!
  Alpha release on 1/14/2011
  Beta release on 3/4/2011
When time is fixed, the things you can adjust are
  Feature (多，好)
  Resource (省)
When we ask for “give me an estimation”
  Estimation of work to be done, or
  Figure out how to hit a target
  These 2 are different

## Slide 13: You can only pick 2 out of 3

## Slide 14: Estimation
Wide-band Delphi
  Lead to greater interaction and more communication among team members
Example:
  Pick a “optimistic” and “pessimistic” candidate
  北京火车站到八达岭长城 (花多长时间)
    外地旅游者，一个大人带两个小孩
  小组步行绕所在城市一周
Notes: Gf might as an extra hour to prepare herself

## Slide 15: Estimation Exercise (1)
Estimate the following things, give a lower bound / upper bound
The length of China mainland border (land border)
  中国陆地边界长度
Population density in of Africa in (ppl / (km)^2)
  非洲人口密度
One year volume of Yangtze River
  长江一年的流量
Surface temperature of the moon (bright side)
  月球表面温度
Total value of RMB in circulation in China, 2009
  2009年中国货币流通的总量
Average number of sentences spoken by a normal person (80 yr old)
  一个80岁的人一生说过多少句话

## Slide 16: For Estimators
2 roles: Estimator, Facilitator
Estimate in hours, be realistic not pessimistic or optimistic
Use one card to write down your estimate, another for your assumptions, only submit the estimation card
After facilitator has entered all the estimates into the spreadsheet, have him enter your assumptions.
Discussion and come to agreement on the assumptions.
Write only your new estimate on a card, submit it
Repeat the last 2 steps until all the estimates converge enough that everyone is happy with the average, or happy to go with the larger estimate.

## Slide 17: Software Development Estimation
The length of China mainland border (land border)
  中国陆地边界长度
That’s just one factor, there is another factor
  如果你们小组要徒步走完所有边界, 你要花多长时间?
2 dimension of factors
  The amount of work (it can change)
  Your ability, determination (it can change, too!)

## Slide 18: Estimation – bottom up
Estimate the cost of one team project!
Too big to estimate?
  Let’s try Divide and Conquer
Estimation – bottom up
  Estimate feature by feature
Target – top down
  We need to release the whole software on DATE1
  It means the testing should be done by DATE2
  It means the coding should be done by DATE3
  It means we should start coding by DATE4
  We’re already behind schedule!

## Slide 19: WBS – Work Break Down
Divide and conquer
Top level (a product)
Mid-level (features) - user perspective
Lower level (feature implementation) – team perspective (PM, Test)
Lowest level (module) – dev perspective

## Slide 20: WBS – different levels
software
Feature1
Sub-feature1
Sub-Feature2
Feature2
UI
Customer
End user
Sub-Feature3
Logic
DB
UI
Logic
DB
UX designer
Dev
Test
Dev
Test
Architect
Dev
Proj mgmt
Design level/PM/Architect
Role (dev/test/designer/PM)

## Slide 21: WBS exercise
WBS your Team project
Coordinator (PM), team member
Coordinator layout the requirement.
Member provides estimation.
Loop
  Analysis, Coordinator lead the team to focus biggest estimation delta
  Estimate again
Coordinator lead the team to consensus
Consensus!
Team report (30 minutes later)

## Slide 22: Roles of each team member
1 PM, N Dev, M Test
Can switch roles after one milestone
Commitment of each team member
  Chicken or Pig
  It’s ok to be a Chicken
  No Parrot
Agile principle:
  Build projects around motivated individuals. Give them the environment and support they need, and trust them to get the job done.

## Slide 23: Group Exercise
We’re in PLANNING STAGE
Work on your vision, project proposal, and success metrics.
30 minutes team working time
Each team report their status (4 projects)
Show your initial round of work items in TFS reports

## Slide 24: Team Report
Your Team project WBS
Estimation of major work items of your team project
Share your WBS of your whole project, in your team blog.
Assign the detail work item to different team members in TFS